## Sheet1
ID | Description | Probability (P) [1-3] | Damage amount (D) [1-3] | Risk score (P*D) | Minimization strategy | Indicators | Emergency plan | Status | Responsible | Updated
1 | Difficulties with portability to other Platforms (e.g. IOS) | 1 | 2 | 2 | - Code with portability in mind - Encapsulate business logic for Kotlin Multiplatform | - Hints in Platform changelogs - Dificullties with PoC implementations | - Write plaftorm code - Neglect platform if not economical | open | Leon | 2025-04-22
2 | Temporary loss of team member (illness, vacation, etc.) | 2 | 1 | 2 | - Communicate and document absence effectively - Include additional time when planing for unforseen events | - Vacation notice - PMs | - Split additonal tasks between remaining team members - Crunch time | open | Jan | 2025-04-22
3 | Development infrastructure outage | 2 | 3 | 6 | - Create backups regularly! - Have alternative provider for each service ready - Simulate worst-case periodically and analyze results | - Notifications from Infrastructure providers - Tech news | - recreate setups - switch infrastructure providers | open | Omar | 2025-04-21
4 | Data loss / corruption | 1 | 3 | 3 | - backup, backup , and backup - RAID setup for critical data | - System alarms | - restore from backup / rollback - analyze incident to prevent similar occurances in the future | open | Leon | 2025-04-22
5 | Lawsuit | 1 | 3 | 3 | - follow all applicable laws - Create Code of Conduct | - Mail | - contact lawyers - investigate | open | Sid | 2025-04-22
6 | Not meeting schedule | 2 | 2 | 4 | - Continually track pace of project - implement time management tools (e.g. burndown chart) | - Sprint retro results | - overtime | open | Omar